Guide 2. APT Project Development

Capstone Course

1. APT Project Progress Summary

Below you will find several fields to complete with the requested information.

| APT project progress summary | Where the project stands MATU closed Phase 1 in week 6 with the product definition, the baseline architecture and the validation with ten caregivers. In Phase 2 the team ran sprint 0, the preparation sprint, which extended from week 7 to week 10 while the development environment and tools were agreed with the instructor. Sprint 1, the first one with product code, starts on Friday 16 October. Activities completed in sprint 0 – ADR-023 closed. With hypothesis H1 refuted (3 out of 10), layer 1 moved from an eight-section care plan to a three-field relief sheet: Their day, If they get upset, and Who to call. – Complete, executable data model. 49 tables, 94 enforced Row Level Security policies and encryption with one key per cared-for person, documented with 13 diagrams and verified with 31 isolation tests against a real PostgreSQL 16 database. – Test strategy v1.1. Test levels, mandatory tests by risk area, pipeline gates and a six-point definition of done. – Backlog for sprints 1 to 3. 21 stories with acceptance criteria, traced to requirements and estimated, reviewed in two rounds and loaded into Trello with their definition of done as a checklist. – Prototype v1.1. 36 screens across 7 user journeys, adjusted to the three-field sheet, plus a clean version for user testing. – Working development repository. Docker Compose with PostgreSQL 16 and Redis 7, a reversible initial Alembic migration, an application connection through a role that cannot bypass RLS, and a green continuous integration pipeline. – Transbank proof of concept, partial. It answered the highest-risk question: deferred capture does not support debit cards. The authorise, partial capture and reversal cases move to sprint 1. Specific objectives achieved – SO1, validate the problem hypotheses: achieved in Phase 1. – SO2, multi-tenant data model: achieved ahead of schedule and beyond the commitment. Ten isolation tests were committed for the end of sprint 1, and at the end of sprint 0 there are 31 running in the pipeline. – SO3 to SO7: not started, with new dates under the adjusted schedule (see Objectives). |
| --- | --- |
| Objectives | General objective (unchanged) To develop a software platform that turns the care plan of an older adult living with dependency into a stock-out forecast for their care supplies and coordinates their replenishment and payment, deployed and running in a demonstration environment by the end of the 2026-2 semester. Adjusted specific objectives The content of the objectives does not change. The dates do, because development started three weeks later than planned and the sprints were regrouped (see Methodology). 1. Validate the seven problem hypotheses with ten interviews and falsification criteria written down before interviewing, by the end of week 6. Achieved. 2. Implement a multi-tenant data model with enforced Row Level Security, verified by isolation tests against a real database. Achieved in sprint 0, with 31 tests. 3. Build the care plan with temporary, revocable relief access, auditing of every access and cryptographic erasure in line with Law 21.719, by 29 October (sprint 2). Previously: sprint 3. 4. Implement the stock-out date calculation and the early alert per supply item, with eight green domain tests, by 5 November (sprint 3). Previously: sprint 5. 5. Deliver the replenishment list, exportable as a document and as a shareable link, working without any commercial agreement, by 12 November (sprint 4). Previously: sprint 6. 6. Build the ordering flow with deferred authorisation and capture for the actual amount, with the seven mandatory payment cases green, by 12 November (sprint 4). For debit cards, plan B of ADR-006 applies. Previously: sprint 7. 7. Deploy the system in a demonstration environment with the six critical user journeys working and the continuous integration pipeline green, by 19 November (sprint 5). Previously: sprint 8. |
| Methodology | What stays the same Scrum adapted to a two-person team, with one-week sprints. Work is split by vertical axis: Jorge Espinoza is Product Owner and owns axis A (care and consumption), and Martín Henríquez is Scrum Master and owns axis B (identity, money and operations). The API contract is agreed before implementation, and if the team falls behind, a declared order of sacrifice applies that never touches the relief sheet, relief access, stock-out forecasting or list export. Adjustments – Schedule. Sprints run from Friday to Thursday: review and retrospective happen on Thursday, and planning on Friday. There are five development sprints between 16 October and 19 November, and two reserve sprints before the final presentation. – AI-assisted development (vibe coding). An assistant generates code, tests and documentation from the team's instructions, and the team reviews, corrects and decides. This lets the team fit into five sprints the scope that was spread over eight. Three controls apply: the definition of done has no exceptions for generated code, the test cases for critical rules are decided by the team, and no real data or secrets are ever given to the assistant. The assumed speed-up factor (1.8) is measured in sprint 1, and if it comes in below 1.4, the order of sacrifice is applied before sprint 2 is planned. – Two repositories. MATU holds the evidence for each phase and the documentation. MATU_PROYECTO holds the code. This keeps the evidence the instructor reviews separate from day-to-day work. – Trello replaces GitHub Projects as the board. Every story has its definition of done as a checklist. – Continuous integration is the objective criterion for done. Every change goes through style checks (ruff), type checks (mypy), secret scanning (detect-secrets), up and down migrations, and tests against a real PostgreSQL database. |
| Progress evidence | Evidence presented 1. Development repository with continuous integration (github.com/MartinHenriquez131/MATU_PROYECTO). Reversible migration, database roles, configuration with no secrets in the code, and a green pipeline. It shows that the project is built through a systematic process, not just code. 2. Implemented data model (MATU repository, docs/modelo-datos.md and docs/diagramas). 49 tables, 94 RLS policies, 13 diagrams and 31 isolation tests. It demonstrates the data modelling competency with a verified design, not an assumed one. 3. Test strategy (docs/estrategia-pruebas.md). It defines what is tested, where the risk lies and when a story is done. 4. Backlog, schedule and sprint 1 plan (docs/backlog-sprints-1-3.md, docs/sprints/ and the Trello board). They show project planning and control with declared capacity and an order of sacrifice. 5. ADR-023 closure (docs/adr/ADR-023-cierre.md). It shows that validation changed the product according to a criterion set before interviewing. 6. Prototype v1.1 (docs/prototipo/). 36 screens that include the three-field sheet and the interview findings. 7. Transbank proof of concept (docs/pruebas-concepto/transbank.md). Partial, with the debit risk already resolved and the pending cases documented. How quality was safeguarded – Isolation tests run against a real database and with the application role, which cannot bypass RLS. A badly written policy fails in the pipeline, not in production. – The migration is verified both ways on every change: up, down and up again. – Secrets are not in the repository. Passwords live in a local .env file, and detect-secrets blocks the change if one appears. – Compliance with Law 21.719 is built into the design: encryption with one key per cared-for person, which enables cryptographic erasure, consent according to the grantor's standing, and auditing of every access. – Decisions are recorded as ADRs, with the alternatives that were discarded. |
| 2. Work Plan Monitoring |  |
| Examine your work plan carefully, focusing especially on the progress status and adjustments columns. |  |

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Activity duration | Owner | Observations | Progress status | Adjustments |
| Requirements engineering · Project assessment and management | Product definition and architecture | Technical documentation, diagramming tools, repository | 6 weeks (weeks 1 to 6) | Both | Helping factor: the design was closed before building. | Completed | No adjustments. |
| Requirements engineering | Problem validation with caregivers | Interview protocol, prototype on a phone, recording sheet | 3 weeks (weeks 3 to 5) | Both | Helping factor: the team's network made it possible to meet the target. Difficulty: three hypotheses fell in the intermediate zone. | Completed | No adjustments. |
| Project assessment and management | Phase 1 presentation | Report, presentation, prototype and appendices | 1 week (week 6) | Both | Helping factor: the scope presented had already been corrected by validation. | Completed | No adjustments. |
| Standards, security and sustainability | Technical setup and payment proof of concept | GitHub Actions, Docker, Alembic, Transbank integration environment | Planned: 1 week (week 7). Actual: weeks 7 to 10 | Martín Henríquez, with Jorge Espinoza | Difficulty: the environment and tools were agreed with the instructor only in week 10. Difficulty: the test payments ended up aborted. | In progress. Repository, environment and pipeline completed. Payment test partial | Extended to week 10. The pending payment test cases move to sprint 1 (16 to 22 October). |
| Information requirements and databases | Data model and multi-tenant isolation | PostgreSQL 16, Alembic, pytest | Planned: sprint 1. Actual: sprint 0 | Martín Henríquez and Jorge Espinoza | Helping factor: writing the model as executable SQL made it possible to test isolation before having an API. | Completed | Brought forward to sprint 0 and exceeded the target: 31 isolation tests instead of 10. |
| Software solutions · Standards, security and sustainability | Layer 1 · Care plan: relief sheet and relief access | Python, FastAPI, PostgreSQL, cryptography library | Planned: 2 weeks (sprints 2 and 3). Adjusted: 1 week (sprint 2, 23 to 29 October) | Jorge Espinoza and Martín Henríquez | Helping factor: backlog with acceptance criteria. Difficulty: it is the sprint with the most estimated hours. | Not started | Sprints 2 and 3 of the plan are merged, with AI-assisted development. First end-to-end product on 29 October. |
| Requirements engineering | Extended validation (4 interviews) | Adjusted protocol, test prototype, recording sheet | 1 week (week 9) | Jorge Espinoza | Difficulty: the sprint 0 extension took up the week. Helping factor: an interviewee offered a contact with a group of relatives. | Delayed | New deadline: before sprint 4 (6 November). It guides the product roadmap beyond the semester without constraining the MVP. |
| Mobile platform development | Family mobile app | Flutter, test devices | Planned: sprint 4. Adjusted: sprint 3 (30 October to 5 November) | Both | Difficulty: learning Flutter. Helping factor: AI assistance with the code. | Not started | Grouped with layer 2 in sprint 3. |
| Software solutions and life cycle | Layer 2 · Consumption and forecasting | Python, ARQ on Redis | Planned: sprint 5. Adjusted: sprint 3 | Jorge Espinoza | Helping factor: it is simple arithmetic on data that layer 1 already holds. | Not started | Brought forward to sprint 3. |
| Software solutions and life cycle | Catalogue and replenishment list | Python, FastAPI, managed platform | Planned: sprint 6. Adjusted: sprint 4 (6 to 12 November) | Jorge Espinoza | Helping factor: exporting the list allows the system to work without a commercial agreement. | Not started | Brought forward to sprint 4. The staging environment is set up earlier, in sprint 3. |
| Mobile platform development · Standards | Usability and accessibility testing | Test prototype, app on a device, task script | Planned: week 13. Adjusted: two rounds | Jorge Espinoza | Helping factor: the clean version of the prototype already exists. | Not started | An early round with the prototype is added before sprint 3, and the second round runs with the app in sprint 4. |
| Software solutions · Standards, security and sustainability | Layer 3 · Order and payment | Transbank Webpay Plus, React with TypeScript | Planned: sprint 7. Adjusted: sprint 4 | Martín Henríquez | Difficulty: debit cards do not support deferred capture. | Not started | Brought forward to sprint 4, with plan B of ADR-006 for debit. |
| Software solutions · Standards, security and sustainability | Close-out, hardening and deployment | Managed platform, load testing tools | Planned: sprint 8. Adjusted: sprint 5 (13 to 19 November) | Both | Difficulty: it overlaps with the final delivery in week 15. | Not started | The demo script and the final report are ready on Monday 16 November. |
| Project assessment and management | Final report and defence | Word processor, presentation tools | Report: week 15. Defence: weeks 17 and 18 | Both | Helping factor: the documentation is kept up to date in the repository. | In progress. Final report draft started | Sprints 6 and 7 remain as reserve before the defence. |
| Project assessment and management | Board, backlog and schedule management (new activity) | Trello, evidence repository | Ongoing, all semester | Martín Henríquez (Scrum Master) and Jorge Espinoza (Product Owner) | Helping factor: the definition of done is on every card. | In progress | Added. The board moves from GitHub Projects to Trello and the schedule to version 1.3. |

3. Adjustments Based on Monitoring

Look more closely at the observations in your work plan. Analyse the planned activities and state which aspects helped or hindered the execution of the plan. Explain how you addressed and/or will address the obstacles. Finally, state the adjustments you made to the work plan as a result of this analysis.

Factors that have helped and/or hindered my work plan: Describe the factors that have helped and/or hindered the development of your APT Project so far. For the difficulties, describe the actions you took and/or will take to solve them.

Helping factors – The design was closed before building. Traced requirements, the data model and the prototype were finished in Phase 1, so sprint 0 was about preparation, not definition. – The data model was written as executable SQL with tests. This made it possible to verify isolation between families without waiting for the API, which is why that activity finished ahead of schedule. – AI-assisted development shortened the time needed for the migration, the pipeline and the documentation in sprint 0. – The backlog has acceptance criteria and a definition of done on every Trello card, so "done" can be verified rather than declared. Hindering factors and how they are being addressed – Development started three weeks late. Sprint 0 ran from week 7 to week 10 while the environment was agreed with the instructor. Action: schedule v1.3 with five development sprints and two reserve sprints, AI-assisted development, and a light sprint 1 to measure the speed-up factor before committing to the rest. – Reduced availability for Jorge. Since 1 October he has been doing his professional internship, about 40 hours a week. Action: his commitment is confirmed at every planning session, and if it drops the order of sacrifice applies, starting with the lowest-value tasks (MATU-28 and MATU-27). – The Transbank proof of concept is incomplete. The test payments ended up aborted. Action: it is diagnosed with a status query script and closed in sprint 1. Payments are only built in sprint 4, so there is room. – Debit cards do not support deferred capture. Action: plan B was already written in ADR-006: with debit, the estimated amount is charged and a credit note is issued for the difference. In sprint 1 the team decides whether to apply it or whether the MVP accepts credit cards only.

Adjusted or removed activities: State the adjustments you made to your work plan or the activities you removed, and justify why. If your work plan has not required and does not require adjustments, justify this decision based on the factors that have allowed you to carry it out as planned.

No activity was removed. The committed scope of 213 hours stays. The adjustments concern the schedule and the way of working: – Sprint 0 extended to week 10. The environment and tools had to be agreed with the instructor before writing product code. – Data model brought forward to sprint 0. Writing it as executable SQL made it testable before having an API, and the highest architectural risk (isolation between families) was verified at the start. – Sprints regrouped from eight to five. Sprints 2 and 3, 4 and 5, and 6 and 7 of the original plan are merged. This is justified by the late start and by AI-assisted development, and it is conditional: if the factor measured in sprint 1 is below 1.4, the order of sacrifice applies before sprint 2. – Staging brought forward to sprint 3, so that the demonstration environment exists two sprints before the close. – Usability in two rounds. The first one uses the test prototype, without waiting for the app, so corrections happen before building. – Payment test shared between both team members, to be closed in sprint 1. – Trello board and two repositories, one for evidence and one for code.

Activities not started or delayed: If you have activities that have not started or are delayed according to your plan, state why you have not been able to meet those deadlines and which strategies you will use to move them forward without affecting your APT project.

Delayed activities – Transbank proof of concept. Reason: the test payments ended up aborted and the cause was not identified. Strategy: diagnosis with the status script, and cases 1, 2, 3 and 5 closed in sprint 1 as priority 0. – Extended validation. Reason: the sprint 0 extension took up week 9. Strategy: four interviews before sprint 4 (6 November), recruited through a concentrated channel. Since cost sharing is already outside the committed scope, its result guides the product roadmap beyond the semester without constraining the MVP. – API skeleton. Reason: it was left pending because the tools were agreed late. Strategy: priority 0 in sprint 1, since the first stories need it. Activities not started Layer 1, the mobile app, layer 2, the catalogue, usability testing, layer 3 and the close-out have not started because they depend on development starting. They have dates in schedule v1.3 and will not affect the project if two conditions hold: the speed-up factor measured in sprint 1 is at least 1.4, and the order of sacrifice is respected. The two reserve sprints (20 November to 3 December) can absorb a delay of up to two weeks without touching the product.